## Traceability Matrix
10 — Requirements Traceability Matrix
Project: Reducing Unplanned Equipment Downtime & Improving Maintenance Reliability ¦ Prepared by: Gagana Suresh ¦ Date: 1 October 2026
Maps every BRD functional requirement (03-BRD-Maintenance-Reporting.md) to its business requirement, user story (07-User-Stories.md), test case (08-Test-Cases.md), and prototype dashboard element.
Dashboard Coverage = Full (dedicated element matching the BRD's display spec) / Partial (relevant but incomplete vs. spec) / None (no element exists) / N/A by design (process/CMMS requirement, not a reporting view).
See 'Open Gaps & Findings' tab for every coverage gap found, with severity and recommended action. See 'Legend & Methodology' tab for full definitions.
FR ID | FR — Short Description | BR ID | Priority | User Stor(y/ies) | Test Case(s) | Dashboard Element (Prototype) | Dashboard Coverage | FR Status Category | FR Status — Detail | Gap Ref
FR-01 | Asset-level cumulative failure/cost rollup, drillable, 6/12/24-month window | BR-01 | Must | US-01, US-02, US-03 | TC-001–TC-013 | "Worst Offenders" worksheet (asset-level, RANK() top-5 highlight) | Partial | Ready | Ready per BRD/backlog. | G1
FR-02 | Failure-mode Pareto, count + cost-weighted, side by side | BR-02 | Must | US-04 | TC-014–TC-017 | "Pareto" worksheet (failure-mode ranking) | Partial | Ready | Ready per BRD/backlog. | G2
FR-03 | Asset-tier segmentation — failure rate and cost, side by side | BR-03 | Must | US-05 | TC-018–TC-020 | "Failure Rate by Tier" + "Downtime Hours by Tier" worksheets | Full | Ready | Ready per BRD/backlog. Cross-checked against Scope-Decisions-and-Limitations-Log locked figures (3.92%/2.77%/2.09%) and matched.
FR-04 | Confidence/traceability disclosure — three-tag badge + drill-down on every figure | BR-01 | Must | US-06 | TC-021–TC-024 | None | None | Ready | Ready per BRD/backlog, but NOT present anywhere in the current Tableau Public prototype. | G3
FR-05 | Planned/unplanned flag at point of work-order entry | BR-01 | Must | US-07 | TC-025–TC-027 | N/A — CMMS data-capture/process requirement, not a reporting view | N/A by design | Blocked | Blocked — BRD §17 Action 1 (frontline validation) and Action 2 (CMMS/IT platform feasibility) both still open. | G6
FR-06 | Corrected repair-duration capture (minimum bar: reassignment flag; stretch: live timestamps) | BR-01 | Must | US-08, US-09 | TC-028–TC-030 | N/A — CMMS data-capture/process requirement, not a reporting view | N/A by design | Blocked | Blocked — BRD §17 Action 1 and Action 2 both still open. | G6
FR-07 | Amber-trend automatic escalation after N consecutive review cycles | BR-06 | Should | US-10 | TC-031–TC-033 | N/A — automated backend rule, not a reporting view | N/A by design | Blocked | Blocked — BRD §17 Action 4 (Reliability Engineer has not yet confirmed the 3-cycle threshold). | G6
FR-08 | Calibration date logged and displayed against sensor ID | BR-06 | Should | US-11 | TC-034–TC-036 | Not built in current prototype (no sensor-level calibration view in Tableau Public build) | None | Ready | Ready per BRD/backlog; simply outside the 4-worksheet prototype's current scope.
FR-09 | Non-disciplinary contributing-factor field at work-order close-out | BR-01 | Should | US-12 | TC-037–TC-038 | N/A — CMMS close-out field, not a reporting view | N/A by design | Blocked | Blocked — Risk 7 / BRD §17 Action 1: no Operations-side stakeholder has reviewed this field yet. | G6
FR-10 | Fixed-plant frequency-only treatment reconciled across all reports | BR-01 | Should | US-13 | TC-039 | Reflected in "Downtime Hours by Tier" (Fixed plant/Ancillary shown without a $ figure, consistent with Option B/C) | Full | Ready | Ready per BRD/backlog.
FR-11 | Preventable-vs-random failure split view (TWF/HDF/PWF/OSF vs. RNF) | BR-04 | Must | US-14 | TC-040–TC-042 | None | None | Ready | Ready per BRD/backlog, but NOT present on the dashboard — despite the underlying figure (97.3% preventable) already being fully computed in EDA-Findings.md. | G4
FR-12 | Torque/tool-wear overstrain threshold display | BR-05 | Should | US-15 | TC-043–TC-045 | None | None | Ready | Ready — Q5 threshold analysis performed 1 Oct 2026 (EDA-Findings.md): tool_wear x torque > tier threshold, 100% precision / 100% recall against the pre-registered 90%/90% bar (98 TP, 0 FP, 0 FN). Gap G5 resolved via real analysis, not relabeling. Display element itself still not built (dashboard coverage: None). | G5 (resolved)
FR-13 | Precursor-pattern classification display (detectable/not detectable/inconclusive) | BR-06 | Should | US-16 | TC-046–TC-048 | None | None | Ready | Ready — Q6 precursor-detectability analysis performed 1 Oct 2026 (EDA-Findings.md): HDF/PWF/OSF Detectable-deterministic, TWF Detectable-probabilistic, RNF correctly Not detectable, all against the same pre-registered 90%/90% bar. Gap G5 resolved via real analysis, not relabeling. Display element itself still not built (dashboard coverage: None). | G5 (resolved)
FR-14 | Simplified, consistent cause-code taxonomy (proposed, not yet adopted) | — (proposed; no BR) | Proposed | US-17 | TC-049 | N/A — proposed CMMS field, not yet adopted into BRD scope | N/A by design | Proposed | Proposed — not yet in BRD. Not counted toward committed engagement scope per 07-User-Stories.md.

## BR & Objective Status
Business Requirement & Charter Objective Status
Cross-references BR-01–BR-06 (03-BRD-Maintenance-Reporting.md §7) against their Charter objective (01-Project-Charter.md §2/§4) and named reviewer.
'# FRs per Matrix tab (formula)' recomputes live from the Traceability Matrix tab — a cross-check that the hardcoded FR list below hasn't drifted from the matrix.
'Objective status' is the Business Analyst's own assessment as of 1 Oct 2026, not a formal sign-off — formal sign-off is tracked separately in 01-Project-Charter.md §4 and 03-BRD-Maintenance-Reporting.md §16.
BR ID | Charter Objective | Reviewer(s) | FR(s) mapped (reference) | # FRs per Matrix tab (formula) | Objective status — honest assessment, 1 Oct 2026
BR-01 | O1 — Quantify total unplanned-downtime hours and cost lost | Finance/Cost Controller | FR-01, FR-04, FR-05, FR-06, FR-09, FR-10 | 6 | Partially met. Mobile-fleet $ figure is complete and reconciled (06-Business-Case.xlsx); Fixed plant/Ancillary remain frequency-only by disclosed decision (Option B/C), not a gap. FR-04's disclosure mechanism (G3) and the four CMMS process FRs (G6) are not yet built. Finance/Cost Controller sign-off not yet obtained.
BR-02 | O2 — Rank failure modes by downtime/cost share (Pareto) | Reliability Engineer | FR-02 | 1 | Partially met. Count-based ranking is dataset-complete and corrected (OSF-undercount fix, 10 Sept). Dashboard shows a single Pareto view, not FR-02's full side-by-side count + cost-weighted + dual-metric spec (G2). Reliability Engineer sign-off not yet obtained.
BR-03 | O3 — Determine which asset tier drives highest failure rate/cost; assess differentiated-investment case | Reliability Engineer + Finance/Cost Controller | FR-03 | 1 | Partially met. Failure rate and cost are reported and displayed per tier (Full dashboard coverage). The differentiated-investment yes/no recommendation itself has NOT yet been formally stated against a pre-agreed materiality threshold, as O3's own success criterion requires — that threshold has not yet been set.
BR-04 | O4 — Quantify preventable vs. random failure proportion | Reliability Engineer | FR-11 | 1 | Data-complete, display-incomplete. 97.3% preventable / multi-flag and RNF caveats are fully computed and documented (EDA-Findings.md). Not yet shown on the dashboard (G4) and not yet reviewed by the Reliability Engineer.
BR-05 | O5 — Test a torque/tool-wear threshold for a proactive replacement policy | Reliability Engineer | FR-12 | 1 | Met, pending formal review. Q5 analysis performed 1 Oct 2026 (EDA-Findings.md): the documented tool_wear x torque overstrain threshold achieves 100% precision / 100% recall against a pre-registered 90%/90% bar (98 TP, 0 FP, 0 FN) — a GO recommendation. This is the Business Analyst's own assessment as of 1 Oct 2026, not a formal sign-off; Reliability Engineer review has not yet been obtained. 07-User-Stories.md and 08-Test-Cases.md's Ready/Executable status is now substantiated — Gap G5 resolved, see Scope-Decisions-and-Limitations-Log.md.
BR-06 | O6 — Identify failure modes with detectable sensor precursor patterns | Reliability Engineer + Project Sponsor | FR-07, FR-08, FR-13 | 3 | Met for 4 of 5 failure modes, pending formal review. Q6 analysis performed 1 Oct 2026 (EDA-Findings.md): HDF and PWF are Detectable-deterministic (100%/100%), OSF likewise (cross-referenced to Q5), TWF is Detectable-probabilistic (93.5% recall, only 5.4% precision — correctly fails the precision leg of the pre-registered bar rather than being forced into a pass), and RNF is correctly Not detectable (the expected null result for a documented ~0.1% random trigger). A new limitation travels with all five results: AI4I's cross-sectional data proves these conditions are distinguishable, not that genuine advance lead time exists. This is the Business Analyst's own assessment as of 1 Oct 2026, not a formal sign-off; Reliability Engineer review has not yet been obtained. FR-07 and FR-08 remain Blocked/unbuilt respectively, independent of this finding.

## Coverage Summary
Coverage Summary
All figures below recompute live from the 'Traceability Matrix' tab (COUNTIF/COUNTIFS formulas) — edit a row there and these numbers update, they are never hardcoded.
Benchmark: 01-Project-Charter.md §4, O0 — 'every functional requirement in the BRD has a corresponding test case and dashboard element in the traceability matrix, with zero orphaned requirements at hand-over.'
Metric | Value
Total functional requirements (FR-01–FR-14) | 14
— Must priority | 7
— Should priority | 6
— Proposed / unprioritized | 1
FRs with at least one User Story | 14 | Target: 100% — every numbered FR must have a backlog story.
FRs with at least one Test Case | 14 | Target: 100% — every numbered FR must have UAT coverage designed.
FR Status — Ready | 9
FR Status — Blocked | 4
FR Status — Proposed | 1
FR Status — See Gap (status itself disputed) | 0 | Expected: 0. FR-12/FR-13 carried this status until Gap G5 was resolved 1 Oct 2026 via real Q5/Q6 analysis — see Scope-Decisions-and-Limitations-Log.md.
Dashboard coverage — Full | 2
Dashboard coverage — Partial | 2
Dashboard coverage — None (ORPHANED per Charter O0) | 5 | This is the headline number against O0's 'zero orphaned requirements' standard. Currently non-zero — see Open Gaps tab.
Dashboard coverage — N/A by design (process/CMMS FRs) | 5 | Not a gap — these FRs change a workflow, not a report, so a dashboard element isn't the right artifact for them.
Must-priority FRs with Full or Partial dashboard coverage | 3 | Out of Must-priority FRs — see next row for the denominator.
Total Must-priority FRs | 7

## Open Gaps & Findings
Open Gaps & Findings
This is the substantive output of building this matrix, not a formality — every row below is a real, specific gap found by cross-checking the BRD against the backlog, the test suite, the dashboard, and the EDA findings against each other.
Severity: High = a Must-level reporting gap, or a cross-document factual inconsistency. Medium = already known/tracked elsewhere, restated here for completeness so this matrix is a genuinely complete picture, not a partial one.
Gap ID | Severity | Requirement(s) / Objective(s) Affected | Description | Recommended Action | Status
G1 | Medium | FR-01 (Must), BR-01 | The prototype's "Worst Offenders" worksheet shows a static top-5 ranked asset view. The BRD's full FR-01 spec requires a 6/12/24-month window selector, a month-over-month trend indicator, and drill-down to source work orders — none of which exist in the Tableau Public prototype. | DECIDED 1 Oct 2026: deferred, not built. Expected and acceptable for a standalone, non-production prototype (Charter §3) — the gap is between 'prototype' and 'production system,' which the Charter already anticipates, not an oversight. State this explicitly in the README/video rather than implying the dashboard is the finished FR-01 capability. | Closed by decision — deferred permanently (out of this engagement's scope per Charter §3), not carried forward as an open task.
G2 | Medium | FR-02 (Must), BR-02 | The dashboard's "Pareto" worksheet shows one ranking (count-based, with the known >100% effect from multi-flag true-occurrence counting). FR-02 requires count and cost-weighted rankings displayed side by side, with neither marked authoritative. | DECIDED 1 Oct 2026: deferred to the Final repo pass (Reconciled-Finish-Schedule.md) alongside G3/G4, since all three require re-opening the Tableau Public workbook in a computer-use session rather than a documentation-only pass. If time allows during that pass, add a second worksheet showing the cost-weighted ranking for Mobile fleet (the only tier with a $ figure); if not, disclose as a named prototype-vs-production-spec gap in the README/video rather than silently implying full FR-02 compliance. | Deferred to Final repo pass — stated reason given, not silently carried forward.
G3 | High | FR-04 (Must), BR-01 | The three-tag (Dataset-derived / Cited source / Labeled assumption) disclosure system — the Financial Controller's own stated non-negotiable standard (BRD §3, §9) — has zero presence anywhere on the dashboard. Tableau Public has no native per-figure tagging/badge mechanism. | DECIDED 1 Oct 2026: deferred to the Final repo pass, not fixed here — this documentation-consistency pass is text-only and has no Tableau Desktop/computer-use access to edit the published workbook. When that pass runs, add a visible caption or annotation on each worksheet naming its data source and tag (e.g., "Failure counts: DATASET (AI4I 2020 re-skinned). Repair-time benchmark: CITED SOURCE, see Assumptions & Sources.") as a lower-fidelity but honest substitute within Tableau Public's real capability, and state in the README/video that full FR-04 badge/drill-down behavior needs a production BI tool beyond this prototype. | Deferred to Final repo pass — High severity, do not drop; stated reason (no dashboard-editing access in this pass) given.
G4 | High | FR-11 (Must), BR-04 | The preventable-vs-random split (97.3% preventable; TWF/HDF/PWF/OSF individually; RNF's labelling-inconsistency caveat) is fully computed and documented in EDA-Findings.md, but has no corresponding dashboard worksheet at all. | DECIDED 1 Oct 2026: deferred to the Final repo pass, same reason as G3 — no Tableau-editing access in this text-only documentation-consistency pass. This is the cheapest of the three dashboard gaps to close once that session runs: the number already exists, nothing new needs to be analyzed, only a 5th worksheet (a stacked bar or KPI tiles) needs to be added. | Deferred to Final repo pass — High severity, do not drop; stated reason given.
G5 | High | FR-12, FR-13 (Should), BR-05, BR-06 — cross-document consistency finding | EDA-Findings.md stated explicitly that Q5 (torque/tool-wear threshold) and Q6 (precursor-pattern detection) had NOT been analyzed yet ("the next layer of EDA work, not answered here"), while 07-User-Stories.md marked US-15/US-16 Status: Ready and 08-Test-Cases.md marked TC-043–048 Executable against that non-existent analysis — a test case cannot genuinely be executable against an analysis that doesn't exist. RESOLVED 1 Oct 2026: the real Q5/Q6 statistical analysis was run against a pre-registered 90% precision / 90% recall bar (fixed before testing, to satisfy Charter O5's anti-bare-correlation requirement), using the real, canonical AI4I 2020 dataset. Q5 (OSF threshold): 100%/100%, GO. Q6: HDF/PWF/OSF Detectable-deterministic, TWF Detectable-probabilistic, RNF correctly Not detectable. Full methodology, results, and a new cross-sectional-vs-longitudinal limitation (the data proves distinguishability, not advance lead time) are recorded in EDA-Findings.md and Scope-Decisions-and-Limitations-Log.md. | Action taken, not merely recommended: Gagana chose to run the real analysis rather than relabel the backlog (option (1) of two options presented). FR-12/FR-13 status updated to Ready in this matrix's Traceability Matrix tab, with detail text naming the specific result; US-15/16 and TC-043–048 are now legitimately substantiated, not just relabeled. Remaining open item: formal Reliability Engineer sign-off on both findings has not yet been obtained — tracked as a BR-05/BR-06 status note on the 'BR & Objective Status' tab, not a new gap. | Resolved — 1 October 2026.
G6 | Medium | FR-05, FR-06, FR-07, FR-09 (Must/Should), BR-01, BR-06 | These are CMMS data-capture/process-change requirements, not reporting views, so "no dashboard element" is correct by design, not a gap. Their real open item is that each remains Blocked pending a validation action already named in the BRD: frontline sign-off and CMMS/IT feasibility (FR-05, FR-06, FR-09), and Reliability Engineer threshold confirmation (FR-07). | DECIDED 1 Oct 2026: deferred by nature, not by oversight — these four FRs are blocked on stakeholder validation (frontline tradespeople, CMMS/IT system owner, Reliability Engineer) that this project's interview phase deliberately did not reach (BRD §17, disclosed scope boundary, not a gap this project can close itself). No new action beyond what BRD §17 Actions 1, 2, and 4, and Risk 7 already specify. | Closed by decision — permanently deferred to a real engagement's next phase; tracked in BRD §17, not carried forward here as if newly open.
G7 | Medium | NFR-05 / AC-6 (BRD §15), US-03 AC3, TC-011 | The finance/ERP reconciliation tolerance that AC-6 requires be agreed with the Financial Controller has not yet been set — it blocks TC-011 from being executable. | DECIDED 1 Oct 2026: deferred by nature, not by oversight — this requires a live Financial Controller negotiation this project's interview phase is already complete and cannot reopen within the current scope. No new action beyond what BRD §17 Action 3 already specifies. | Closed by decision — permanently deferred to a real engagement's next phase; tracked in BRD §17, not carried forward here as if newly open.
G8 | Medium | Dashboard (all failure-mode labels), 09-Benefit-Realization-Report.md §8 | The dashboard's full failure-mode names (HDF = Heat dissipation, OSF = Overstrain, PWF = Power, TWF = Tool wear, RNF = Random) had not yet been verified against the actual AI4I 2020 source documentation — carried forward three times since 30 Sept 2026. | RESOLVED 1 Oct 2026, as a direct by-product of sourcing the Q5/Q6 analysis: verified all five full names directly against the dataset's own documented generation mechanism (Matzka, S. (2020), IEEE AI4I, doi.org/10.1109/AI4I49448.2020.00023). All five names match the dashboard's existing labels exactly — no rebuild or relabeling needed. | Resolved — 1 October 2026. See Reconciled-Finish-Schedule.md and Scope-Decisions-and-Limitations-Log.md for the full record.

## Legend & Methodology
Legend & Methodology
How to read every tab in this workbook.
Technique used to build this document (for the Prompt Library)
Technique | Chain-of-thought cross-document reconciliation: every FR was traced forward (does a story exist? a test case? a dashboard element?) and every claimed 'Ready'/'Executable' status was traced backward against the document it actually depends on (does the underlying analysis or data genuinely exist?). The backward pass is what surfaced G5 — a real inconsistency, not a hypothetical one.
Dashboard Coverage column
Full | A dedicated dashboard element exists and matches the BRD's display requirement for that FR.
Partial | A dashboard element exists and is relevant, but does not meet the BRD's full spec for that FR (e.g., missing a sub-feature such as drill-down or a second ranking).
None | No dashboard element exists for this FR at all, and the FR is a reporting/display requirement (so one should exist).
N/A by design | This FR changes a workflow or data-capture process, not a report — it was never meant to produce a dashboard element. Not a gap.
FR Status Category column
Ready | No open validation gap blocks build, per 07-User-Stories.md.
Blocked | A named BRD §17 action or Risk explicitly holds this requirement from build — see the Status Detail column for the exact citation.
Proposed | Not yet a numbered BRD requirement (FR-14 only) — tracked for visibility, not counted toward committed scope.
See Gap | The status itself is disputed by this matrix's cross-check — see the named Gap in the Open Gaps tab before trusting the backlog's own label.
Scope note — why some gaps are expected, not defects
Prototype vs. production | 01-Project-Charter.md §3 explicitly scopes the dashboard as a "standalone prototype dashboard built against a static extract... explicitly not a live, CMMS-integrated production tool." Gaps G1 and G2 are the expected distance between a prototype and the BRD's full production-grade spec — they are disclosed here, not hidden, consistent with this project's standing data-integrity rule.
Must-level ≠ automatically built | A requirement being Must-priority means it was validated as necessary — it does not mean it has already been built. G3 and G4 are both Must-level requirements that are validated, scoped, and simply not yet implemented in this specific prototype iteration.
Related documents
Source of FR/BR definitions | 03-BRD-Maintenance-Reporting.md v2, Section 7 (BRs) and Section 8 (FRs).
Source of User Stories | 07-User-Stories.md, 28 Sept 2026 — 17 stories across 8 epics.
Source of Test Cases | 08-Test-Cases.md, 30 Sept 2026 — 49 test cases.
Source of dashboard scope | Reconciled-Finish-Schedule.md (dashboard rebuild entry, 30 Sept 2026) and the Tableau Public workbook itself.
Source of EDA findings | EDA-Findings.md, last updated 1 Oct 2026 — Q1–Q6 all answered. Q5/Q6 were added 1 Oct 2026 via real statistical analysis against a pre-registered bar, closing Gap G5.